## Dashboard
TripWise Enhanced Implementation Status
Assignment | Enhanced Implementation - Partial Submission (Part One)
Due Date | 2026-07-05 11:59 PM
Status | Complete through July 6
Primary Enhancements | Functional tabs, typed city/state inputs, autocomplete, itinerary tab, vacation design
Completion Target | All enhancement tasks marked complete by July 6
Submission Readiness | Ready for Canvas after GitHub/screenshots are verified
Deliverable | Required? | Status | Completed Date | Evidence / File | Notes | Owner | Priority
AI prompts | Yes | Complete | 2026-07-01 | AI_Prompts_Vacation_Update.txt | Updated to match enhanced website changes | Josh | High
Code | Yes | Complete | 2026-07-01 | index.html, styles.css, app.js | All tabs functional; itinerary and typed city/state fields added | Josh | High
Screenshots | Yes | Complete | 2026-07-02 | Updated screenshots | Show trip overview and itinerary success | Josh | High
Enhancement document | Yes | Complete | 2026-07-03 | Enhanced Implementation Document | Explains modifications, results, and comparison | Josh | High
Operational flowchart | Yes | Complete | 2026-07-03 | TripWise_Enhanced_Operational_Flow_Updated.png | Color-coded modifications | Josh | High
Technical design flowchart | Yes | Complete | 2026-07-03 | TripWise_Enhanced_Technical_Design_Flow_Updated.png | Color-coded technical modifications | Josh | High
Updated Gantt chart | Yes | Complete | 2026-07-04 | Updated Gantt sheet | Everything through July 6 marked complete | Josh | High
Critical Path Analysis | Yes | Complete | 2026-07-04 | Critical Path sheet | A-B-C-D-E-F path complete | Josh | High
PERT chart | Yes | Complete | 2026-07-04 | PERT Analysis sheet + image | Enhanced tasks updated | Josh | High
Self-reflection recording | Yes | Pending Recording | 2026-07-06 | VoiceThread/Kaltura recording | Needs final recording upload | Josh | High

## Updated Gantt
TripWise Enhanced Implementation Gantt Chart - Complete Through July 6
ID | Task | Start | End | Duration | Dependency | Owner | Status | % Complete | Critical? | Enhanced Change | Evidence | 6/29 | 6/30 | 7/1 | 7/2 | 7/3 | 7/4 | 7/5 | 7/6 | Status
A | Review enhanced requirements | 2026-06-29 | 2026-06-30 | 2 | None | Josh | Complete | 100% | Yes | Confirmed Part One deliverables and scope | Assignment checklist | [8 empty] | Complete | bar: 6/29 to 6/30
B | Update UI and tabs | 2026-06-30 | 2026-07-01 | 2 | A | Josh | Complete | 100% | Yes | Removed Implementation Demo; added Itinerary tab | index.html | [8 empty] | Complete | bar: 6/30 to 7/1
C | Add typed city/state input + autocomplete | 2026-07-01 | 2026-07-02 | 2 | B | Josh | Complete | 100% | Yes | Replaced fixed dropdown-only cities with typeable fields and datalist | index.html / app.js | [8 empty] | Complete | bar: 7/1 to 7/2
D | Enhance recommendation engine | 2026-07-02 | 2026-07-04 | 3 | C | Josh | Complete | 100% | Yes | Preference weighting for cost, speed, flexibility, comfort | app.js | [8 empty] | Complete | bar: 7/2 to 7/4
E | Add itinerary + vacation design | 2026-07-03 | 2026-07-05 | 3 | D | Josh | Complete | 100% | Yes | Generated itinerary, checklist, more colorful vacation UI | index.html / styles.css / app.js | [8 empty] | Complete | bar: 7/3 to 7/5
F | Test tabs, calculations, screenshots | 2026-07-05 | 2026-07-06 | 2 | E | Josh | Complete | 100% | Yes | Verified all pages and captured screenshots | Screenshots | [8 empty] | Complete | bar: 7/5 to 7/6
G | Update document and flowcharts | 2026-07-03 | 2026-07-06 | 4 | D | Josh | Complete | 100% | No | Color-coded operational and design flowcharts | DOCX + PNG flowcharts | [8 empty] | Complete | bar: 7/3 to 7/6
H | Update Gantt/Critical Path/PERT | 2026-07-04 | 2026-07-06 | 3 | G | Josh | Complete | 100% | No | Marked all tasks through July 6 complete | This workbook | [8 empty] | Complete | bar: 7/4 to 7/6
I | GitHub upload and final Canvas prep | 2026-07-06 | 2026-07-06 | 1 | F,H | Josh | Complete | 100% | No | Upload updated code and submit links | GitHub/Canvas | [8 empty] | Complete | bar: 7/6

## Critical Path
TripWise Enhanced Critical Path Analysis
Activity | Task | Duration | Predecessor | Early Start | Early Finish | Status | Critical Path?
A | Requirements Review | 2 | None | 0 | 2 | Complete | Yes
B | UI Enhancements | 2 | A | 2 | 4 | Complete | Yes
C | Typed Inputs + Autocomplete | 2 | B | 4 | 6 | Complete | Yes
D | Preference Decision Engine | 3 | C | 6 | 9 | Complete | Yes
E | Itinerary + Vacation UI | 3 | D | 9 | 12 | Complete | Yes
F | Testing + Screenshots | 2 | E | 12 | 14 | Complete | Yes
G | Final Docs + Flowcharts | 4 | D | 9 | 13 | Complete | No
H | Gantt / PERT / Submission Prep | 3 | G | 13 | 16 | Complete | No
Critical Path | A → B → C → D → E → F
Total Critical Duration | 14 days
Completion Status | All required enhanced implementation tasks through July 6 are complete.
Risk Note | Only final recording/upload verification should be completed after artifacts are uploaded.

## PERT Analysis
TripWise Enhanced PERT Analysis
Activity | Task | Optimistic | Most Likely | Pessimistic | Expected Time | Status | Notes
A | Requirements Review | 1 | 2 | 3 | 2 | Complete | Assignment scope confirmed
B | UI Enhancements | 1 | 2 | 3 | 2 | Complete | Tabs revised
C | Typed Inputs + Autocomplete | 1 | 2 | 3 | 2 | Complete | City/state typing added
D | Preference Decision Engine | 2 | 3 | 5 | 3.1667 | Complete | Weighted scoring added
E | Itinerary + Vacation UI | 2 | 3 | 5 | 3.1667 | Complete | Itinerary tab and lively style added
F | Testing + Screenshots | 1 | 2 | 3 | 2 | Complete | Screenshots completed
G | Final Docs + Flowcharts | 2 | 4 | 5 | 3.8333 | Complete | Color-coded charts
H | Gantt / PERT / Submission Prep | 1 | 3 | 4 | 2.8333 | Complete | Workbook updated
PERT Summary
All enhancement tasks through July 6 | Complete
Primary risk mitigated | Scope drift reduced by removing Implementation Demo tab and focusing on itinerary/planning utility.
Critical deliverable status | Flowcharts, Gantt, PERT, code, screenshots, and documentation updated.

## Enhancement Change Log
TripWise Enhanced Change Log - What Changed From Simple Implementation
Change ID | Previous Version | Enhanced Version | Modification Type | Color Code | Result | Status
CH-1 | Implementation Demo tab included | Removed and replaced with Itinerary tab | New/removed UI tab | Green | Website is more useful for travelers | Complete
CH-2 | City fields were limited dropdowns | Origin/destination can be typed with autocomplete suggestions | Input enhancement | Green | Users can enter any city/state | Complete
CH-3 | Basic recommendation only | Weighted decision engine using cost, speed, flexibility, comfort | Modified logic | Orange | Recommendation is more personalized | Complete
CH-4 | Basic dashboard style | More colorful vacation-style interface | UI enhancement | Green | Website feels more lively and travel-focused | Complete
CH-5 | Hotel/stops were simple cards | Hotel, pit stops, timeline, checklist, and itinerary added | Feature enhancement | Green | TripWise acts as a planning tool, not just a calculator | Complete
CH-6 | Limited evidence/screenshots | Updated screenshots and flowcharts show changes | Documentation enhancement | Blue | Submission better matches Part One deliverables | Complete