## Dashboard
RouteWise Compass - Updated Submission Evidence
Project Name | RouteWise Compass
Enhancement Focus | Multi-mode travel decision app: drive, fly, train, bus, bike, and mixed travel
Main Update | Added expert travel planning, USA map preview, curated stops/stays/explore pages, screenshots, and updated project management artifacts
Status | Complete
Submission Date | 2026-07-12
Package | RouteWise_Compass_Full_Submission_Evidence_Package.zip
Deliverable | File / Evidence | Status | Owner | Due Date | Completed Date | Notes | Priority
Updated website | RouteWise_Compass_Expert_Planner.zip | Complete | Josh | 2026-07-12 | 2026-07-12 | Frontend, optional backend, README, prompts | High
Screenshots | RouteWise_Compass_Screenshots folder | Complete | Josh | 2026-07-12 | 2026-07-12 | 8 screenshots for key pages | High
Updated Gantt Chart | Updated Gantt sheet | Complete | Josh | 2026-07-12 | 2026-07-12 | Tasks updated for RouteWise Compass | High
Critical Path Analysis | Critical Path Analysis sheet | Complete | Josh | 2026-07-12 | 2026-07-12 | Critical path A-H marked complete | High
PERT Chart | PERT Analysis sheet + PNG | Complete | Josh | 2026-07-12 | 2026-07-12 | Expected time and variance included | High
USA Map Evidence | 03_USA_Map_Route.png | Complete | Josh | 2026-07-12 | 2026-07-12 | Shows route preview visually | High
Stops/Stays Evidence | 06_Stops_Stays.png | Complete | Josh | 2026-07-12 | 2026-07-12 | Specific places, where, and why | High
Explore Evidence | 07_Explore_Nearby.png | Complete | Josh | 2026-07-12 | 2026-07-12 | Route/destination logic; fly mode destination-only | High

## Updated Gantt
RouteWise Compass Updated Gantt Chart
ID | Task | Start | End | Duration | Dependency | Owner | Status | % Complete | Critical? | Deliverable Area | Output Evidence | Notes | 7/8 | 7/9 | 7/10 | 7/11 | 7/12 | Status
A | Confirm enhanced RouteWise Compass scope | 2026-07-08 | 2026-07-08 | 1 | None | Josh | Complete | 100% | Yes | Planning | Requirements updated | Moved beyond drive/fly | ■ |  |  |  |  | Complete
B | Redesign frontend layout, colors, and UX | 2026-07-08 | 2026-07-09 | 2 | A | Josh | Complete | 100% | Yes | Frontend | index.html, styles.css | Less bland, more usable | ■ | ■ |  |  |  | Complete
C | Build multi-mode decision engine | 2026-07-09 | 2026-07-10 | 2 | B | Josh | Complete | 100% | Yes | Logic | app.js | Drive/fly/train/bus/bike/mixed scoring |  | ■ | ■ |  |  | Complete
D | Add curated stops, stays, and explore data | 2026-07-10 | 2026-07-11 | 2 | C | Josh | Complete | 100% | Yes | Content | routeData.js | Specific places, where, why |  |  | ■ | ■ |  | Complete
E | Replace weak map with USA route preview | 2026-07-11 | 2026-07-11 | 1 | D | Josh | Complete | 100% | Yes | Map | USA Map page | Visual start/destination/route/stops |  |  |  | ■ |  | Complete
F | Test pages and create screenshots | 2026-07-12 | 2026-07-12 | 1 | E | Josh | Complete | 100% | Yes | Evidence | 8 screenshot PNGs | Screenshots for Canvas |  |  |  |  | ■ | Complete
G | Update Gantt, Critical Path, and PERT | 2026-07-12 | 2026-07-12 | 1 | F | Josh | Complete | 100% | Yes | Project Management | This workbook | Required artifact |  |  |  |  | ■ | Complete
H | Package final files for submission | 2026-07-12 | 2026-07-12 | 1 | G | Josh | Complete | 100% | Yes | Submission | Evidence package ZIP | Website + evidence |  |  |  |  | ■ | Complete

## Critical Path Analysis
RouteWise Compass Critical Path Analysis
Activity | Task | Duration | Predecessor | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical?
A | Confirm enhanced scope | 1 | None | 0 | 1 | 0 | 1 | 0 | Yes
B | Redesign frontend | 2 | A | 1 | 3 | 1 | 3 | 0 | Yes
C | Build decision engine | 2 | B | 3 | 5 | 3 | 5 | 0 | Yes
D | Curated content/data | 2 | C | 5 | 7 | 5 | 7 | 0 | Yes
E | USA map preview | 1 | D | 7 | 8 | 7 | 8 | 0 | Yes
F | Screenshots/testing | 1 | E | 8 | 9 | 8 | 9 | 0 | Yes
G | Gantt/CPA/PERT | 1 | F | 9 | 10 | 9 | 10 | 0 | Yes
H | Final package | 1 | G | 10 | 11 | 10 | 11 | 0 | Yes
Critical Path | A → B → C → D → E → F → G → H
Total Project Duration | 11 task-days
Slack | 0 for all required submission tasks
Conclusion | The project is complete and evidence is ready for Canvas submission.

## PERT Analysis
RouteWise Compass PERT Analysis
Activity | Task | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | Predecessor | Status | Critical?
A | Confirm enhanced scope | 1 | 1 | 2 | 1.1667 | 0.027778 | None | Complete | Yes
B | Redesign frontend | 1 | 2 | 3 | 2 | 0.11111 | A | Complete | Yes
C | Build decision engine | 1 | 2 | 3 | 2 | 0.11111 | B | Complete | Yes
D | Curated stops/stays/explore data | 1 | 2 | 4 | 2.1667 | 0.25 | C | Complete | Yes
E | USA map preview | 1 | 1 | 2 | 1.1667 | 0.027778 | D | Complete | Yes
F | Screenshots/testing | 1 | 1 | 2 | 1.1667 | 0.027778 | E | Complete | Yes
G | Gantt/CPA/PERT | 1 | 1 | 2 | 1.1667 | 0.027778 | F | Complete | Yes
H | Final package | 1 | 1 | 2 | 1.1667 | 0.027778 | G | Complete | Yes
PERT Chart Image | RouteWise_Compass_PERT_Critical_Path.png
PERT Summary | All tasks are complete; routeData and screenshot evidence lowered submission risk.
Main Risk Controlled | Canvas may reject ZIP; individual files are also provided.
Conclusion | Updated project management artifacts are ready.

## Screenshot Evidence
RouteWise Compass Screenshot Evidence
Screenshot | Page | Purpose | File Name | Status | Notes
1 | Trip Inputs | Shows user inputs and decision priorities | 01_Trip_Inputs.png | Complete | State/city, budget, days, sliders
2 | Travel Advisor | Shows recommendation and reasoning | 02_Travel_Advisor.png | Complete | Best plan and why
3 | USA Map | Shows USA map route preview | 03_USA_Map_Route.png | Complete | Start/destination/stops
4 | Compare Options | Shows mode comparison | 04_Compare_Options.png | Complete | Drive/fly/train/bus/bike/mixed
5 | Itinerary | Shows recommended itinerary | 05_Itinerary.png | Complete | Step-by-step plan
6 | Stops + Stays | Shows specific stops/stays | 06_Stops_Stays.png | Complete | Where + why
7 | Explore Nearby | Shows things to see | 07_Explore_Nearby.png | Complete | Route + destination / fly destination-only
8 | Packing + Safety | Shows checklist | 08_Packing_Safety.png | Complete | Safety and backup planning

## Change Log
RouteWise Compass Enhancement Change Log
Change ID | Old Issue | Updated Change | Reason | Result | Evidence | Status | Color Code
CH-1 | Website looked bland | Redesigned with RouteWise Compass style and stronger layout | Make it feel like a real app | Improved usability and presentation | Screenshots 1-8 | Complete | Green
CH-2 | Map looked weak | Added USA map-style route preview | Users need visual route context | Start, stop, destination, route line shown | Screenshot 3 | Complete | Green
CH-3 | Stops/stays too generic | Added specific stop/stay names with where and why | Make guidance useful | Traveler knows what to actually do | Screenshot 6 | Complete | Green
CH-4 | Explore page inaccurate for fly | Fly mode now shows destination-only attractions | Flying skips road stops | Explore logic is mode-aware | Screenshot 7 | Complete | Orange
CH-5 | Only drive/fly focus | Expanded to drive, fly, train, bus, bike, mixed | Match concept | Better decision options | Screenshot 4 | Complete | Green
CH-6 | Missing submission evidence | Added screenshots, Gantt, CPA, PERT | Canvas deliverables require it | Full evidence package ready | Workbook + PNGs | Complete | Green